## Sheet1
Table 1. Summary of Projected Activities
Activity | February |  | March |  |  |  | April |  |  |  | May
| 19-23 | 26-28 | 3-7 | 10-14 | 17-21 | 24-28 | 31-4 | 7-11 | 14-18 | 21-25 | 28-2 | 5-9 | 12-13
Revise draft proposal
Submit final proposal
Obtain secondary data
Conduct interviews
Analyze data
Create spatial database
Ground-truth study area
Prepare draft report
Submit draft report
Revise draft report
Present
Submit final Report